## Open Items
Business Practices Subcommittee Action Items
Issue # | Status | Description | Assigned to | Dates
| Open |  |  |  |  | Meeting
| Closed |  |  |  |  | When will
| Hold |  |  | Assigned | Due | be Addressed
4 | Hold | Talk to the ORS about what data is needed to start the parallel test | TBD/Tom Mallinger | 2010-12-01 |  |  | Need to explain what is currently available? What data is planned to be provided and when? What data will not be provided under the Parallel Flow Visualization Interim Solution? 2/16 Will keep this item open until the metrics (Commercial and Reliability Metrics are defined) 6/14 - Will need to define evaluation criteria. 7/18/12 - Evaluation criteria will be developed after standards have been developed.
47 | Hold | Define WEQ BPS Evaluation Criteria for PFV Permanent Solution | TBD | 2011-04-13 | TBD |  | 4/28 - A representative from the Parliamentary Committee, or perhaps NAESB, will address NAESB's role in metrics development and field tests at the May WEQ BPS meeting 6/8 - Description was changed from developing "metrics" to developing "evaluation criteria" based BPS disucssion with Rae McQuade on May 17th. 9/13 - The evaluation criteria will be developed after the business practice standards are finalized
57 | Closed | Begin developing approaches "strawman" for issues documented in Appendix A of the Parallel Flow Visualization Permanent Solution Work Paper. | Tom Mallinger, Chris Advena, Nelson Muller, Bert Bressers, Steve Sanders, Blaine Erhardt | 2011-06-15 |  | 08/2012 09/2012 | 7/18/12 - Two remaining items are subpriorities and reloading. Subpriorities update will be brought to the full BPS at the August meeting. The specific GTL flows reloading will be brought back to the full BPS meeting at the September meeting. The sub-team needs to have further discussion on general reloading. 08/15/12 - Sub-team met on July 30th to review subpriorities and have requested a conference call with the full subcommittee be set between the August and September BPS meeting to walk through examples. Conference Call has been scheduled for August 27th from 9:00 - 12:00 (Central) to review examples. Work paper is to be posted prior to the meeting. 9/12 - The subteam work on subpriorities has been completed 10/17 - The subcommittee agreed this item could be closed. There are separate Action Items for Reloading (113) and Coordinated Flowgate Tests (100).
95 | Open | Develop draft recommendation to be reviewed by the subcommittee. | Narinder Saini Ed Skiba Alan Pritchard JT Wood | 2012-05-17 |  | 2012-11-14 | Provide a status update at the June 13-14 Meeting. 7/18/12 - Status update will be provided on July 18th. 8/16/12 - Updates were provided to the BPS and the BPS provided direction to the subteam in a number of areas. The next update will be provided at the September meeting. 10/18/12 - The subteam walked through at a high level changes that were made since the last review with the subcommittee. Additional updates will be made to the recommendation for the November meeting.
96 | Open | Review item 6 from "SPP_Issues_For Evaluation During Full Staffing_2012-2013 (revised 06-13-2012)" to detemine if changes are needed to the white paper. | Nelson Muller Tom Mallinger Neil Shah Bert Bressers | 2012-06-13 |  | 2012-11-14 | 7/18/12 - Item will be discussed at the August 2012 meeting. 8/15/12 - Item has not been reviewed. Moved date to be addressed to September meeting. 10/17/12 - Tom, Neil, Nelson, and Bert will have a call to discuss the issue and appendices in Change Order 283. Tom will schedule the call and report back to the subcommittee at the November meeting.
100 | Open | The subteam working on the remaining credit for redispatch items will develop minimum criteria for determining coordinated flowgates. | Chris Advena | 2012-07-18 |  | 2012-11-14 | 7/18/12 - Subteam is combination of BPS members and IDCWG members. 10/17/12 - Frank Koza to follow-up with Chris Advena for a status update. 10/18/12 - Chris is revising the draft document which will be reviewed by another group before it is brought back to the BPS.
106 | Closed | Add note to the whitepaper indicating that the subcommittee decided to move forward with the LSE tagging all pseudo ties and dropping the option not to tag in the Pseudo Tie requirements for Generator Prioritization. | E. Skiba | 2012-08-16 |  | 2012-09-12 | 10/17/12 - Ed made the update to the Whitepaper. However, there was discussion in the September meeting to look at the treatment of pseudo-ties for those sink BAs that elected to use the Generator Priorization Method. As a result Action Item 115 was created. The subcommittee agreed this item could be closed.
107 | Closed | Verify with the IDCWG that a pseudo tie tag will not require a pseudo BA on the tag. | N. Saini | 2012-08-16 |  | 2012-09-12 | 10/17 - Narinder verified that a pseudo-BA is not required for a pseudo-tie tag.
110 | Open | Develop NERC Support document for the PFV Recommendation | E. Skiba N. Saini | 2012-07-19 |  | 2012-10-14 | 10/18 - Document needs to be updated to remove SDX references since the SDX will transition to the Consortium on April 1, 2013.
111 | Open | Develop IDC Support document for the PFV Recommendation | F. Koza N. Muller R. Thappetaobula Y. Bahbaz | 2012-07-19 |  | TBD | 10/17 - IDCWG will provide a user guide and then subteam can redline the user guide to reflect the changes.
113 | Closed | Develop proposed language for WEQ-008.3.3 - 3.7 to allow an RC to set a max target total flow while using WEQ-008 language for reloads TLR levels 3 - 5. | B. Bressers | 2012-09-12 |  |  | 10/17/12 - Based on Bert's review there are no changes needed to WEQ-008. There may need to be changes to the IDC.
114 | Closed | If information readily available, TVA, MISO, SPP and PJM to review coordinated flowgates study process to identify the number of coordinated flowgates identified using the IDC base case test v. the number using offline studies | T. Mallinger B. Bressers C. Advena E. Skiba | 2012-09-12 |  | 2012-10-17 | 9/12 - Ed to follow up with Marshala Green at TVA 10/17 - TVA did not have this information readily available, MISO information is not readily available. SPP 6 out of 65 coordinated flowgates, on another party's system were identified though the IDC Base Case Test. Using the numbers Bert provided it does not appear that the single IDC Base Case Test will be sufficient to identify coordinated flowgates.
115 | Open | Drive out the detail on treatment of all BAs impacted by pseudo-ties for a sink BA elects to use the generator prioritization method and opts not to tag the pseudo tie. | E. Skiba T. Mallinger B. Bressers | 2012-09-12 |  | 2012-10-17 | 9/12 - A status report will be provided at the October meeting. Draft language by November meeting. 10/18/12 - Subcommittee determined that this item should be kept open until the discussions are held with JESS about using the e-tagging application for submitting generator priority schedules. Additional work on this item has been placed on hold pending the outcome of the discussions with JESS.
116 | Open | Initiate discussions with JESS to determine if e-tagging application could be used for entering generator priority schedules. | E. Skiba | 2012-10-18 |  | 2012-11-14 | Ed will talk with the JESS about using the e-tagging application to submit Generator Priority Schedules with the understanding that the Energy Profiles on Generator Priority Schedules would be blank or omitted from the tags. What timing requirements and NERC standards requirements/obligations would apply if the BPS uses the e-tagging for submitting generator priority schedules? Can the system handle the increased volume of tags? Possibly 5,000 – 10,000 more tags for the Eastern Interconnection?
117 | Open | Talk to Jim Castle to determine if NYISO would be willing to make more than summary data available to TSPs during Parallel Flow Visualization full staffing (parallel test) | E. Skiba | 2012-10-18 |  | 2012-11-14
118 |  | Next number to be assigned

## Closed Items
Business Practices Subcommittee Action Items
Issue # | Status | Description | Assigned to | Dates |  |  | Notes
| Open |  |  |  |  | Meeting
| Closed |  |  |  |  | When will
| Hold |  |  | Assigned | Due | be Addressed
1 | Closed | Develop Project Plan/Schedule to complete Parallel Flow Visualization Permanent Solution. | Ed Skiba | 2010-12-01 | 2011-02-09 | 2011-02-16 | 02/03 - Draft Project Plan was posted.
2 | Closed | Review Project Plan/Schedule with Subcommittee | Ed Skiba | 2010-12-01 | 2011-02-16 | 2011-02-16
3 | Closed | Talk to the ORS about the Parallel Flow Visualization Parallel Test Start Date and duration of the Field Test | TBD/Tom Mallinger | 2010-12-01 | 2011-02-16 | 2011-02-16 | (Does the test start with full load of data for change order 283, BA supplied data for NAESB Interim Solution, or when permanent solution is implemented. Does the field test have to be 12-18 months.
5 | Closed | How will the data be integrated to show how curtailments would be assigned in the production/test systems | Nelson Muller | 2010-12-01 |  |  | The user interfaces are still to be defined. 5/17 - IDCWG created task force to define display 6/14 - Since the BPS selected the Hybrid option the IDC Task Force can begin their work. The next IDC meeting will not occur before the July BPS meeting. 6/14 - Nelson will ask Yasser and Larry Kezele to add to next IDCWG Agenda. 7/12 - Nelson has requested this be added to the next IDC Agenda. 9/13 - The IDCWG has assigned a task force to develop this issue. 10/12 - Ongoing updates will be provided to the BPS from the IDC Chair. The expectation is the changes to reflect how curtailments would be assigned in the production/test systems will be implemented as part of the permanent solution. 7/18/12 - Agenda item will be added to August IDCWG meeting to discuss data integration and user interface for PFV. 9/12 - The IDC is looking to provide info to people w/appropriate access to see somewhat in real time the impacts of the TLR relief obligation in the production environment and the PFV/GTL test environment
6 | Closed | IDC Working Group to submit Standards Request to NAESB to address issue Reallocation under TLR Level 5B so that reallocation occurs under 5B similar to how it occurs under 3B. | Nelson Muller/IDC Working Group | 2010-12-01 |  |  | The expectation is this item once triaged will be assigned to the BPS. This item is not required to move forward with the Parallel Flow Visualization Interim Solution. 1/11 - Nelson will check to see if someone from the IDCWG wants to take the lead in developing the standards request. 2/16 - Larry to follow up at next IDC Meeting to determine if someone in the IDC wants to submit a NAESB Standards Request. Ed to send Larry the template for NAESB Standards Request. James Culliton offered NAESB support if there are questions with completing the form. 2/18 - Template was sent to Larry Kezelle. 4/11 - IDCWG agreed that they will be sumitting a Standards request to NAESB for reallocation of TLR Level 5B. 6/14 - Nelson will ask Yasser and Larry Kezele to add to next IDCWG Agenda. 7/12 - Nelson will bring up issue at the next IDC WG Meeting. 9/13 - the IDCWG has been working on this issue through drafting a standard. This item will be placed on the agenda for the October 11-12 joint IDCWG/BPS meeting 10/12 - Draft standards request has been developed by the IDCWG. The IDCWG Chair will contact the NAESB office regarding questions on how to complete the Standards Request. An update on the request will be provided at the November BPS Meeting. 1/4/12 - Standards Request was submitted to NAESB in early December (R11020 is available at: http://www.naesb.org/pdf4/r11020.doc)
7 | Closed | Provide IDC Working Group with BPS 2011 Meeting Calendar. | Ed Skiba | 2010-12-01 | 2010-12-10 | N/A | Calendar was provided to IDCWG Chair.
8 | Closed | Confirm if February 16th will be a Joint BPS/IDC WG Meeting | Nelson Muller | 2010-12-01 | 2011-01-11 | 2011-02-16 | Nelson to confirm if February meeting will be a joint meeting. 02/03 - IDCWG members have been requested to dial into February 16-17 BPS meeting based on agenda items.
9 | Closed | Update First to Curtail/Last to Curtail Examples based on December 1st BPS Meeting | Ed Skiba | 2010-12-01 | 2010-12-10 | 2011-01-11 | Include definitions for Parallel Flow and Seams Agreement 01/11/11 -Documents were provide (updated examples and two-tier curtailment document) There are still open issues as to whether there is sufficient detail as to what is required in a Seams Agreement. The subcommittee agreed to close this item.
10 | Closed | Develop paper describing 2-tier firm curtailment approach for input to FERC staff requesting guidance from staff on whether two-tier curtailments would be considered a policy issue to be addressed by FERC. | Ed Skiba Jim Busbin Steve Sanders Tom Mallinger Nelson Muller Bert Bressers | 2010-12-01 | 2011-01-11 | 2011-01-11 | Subcommittee members have requested one round of comments/updates be applied to document. Task Group will work toward this goal but recognizes time constraints due to upcoming holidays/vacations. Decision was made to only include simple approach. (Will not include Flowgate Allocation second pass two-tier curtailment). 1/11/11 - Initlal draft was provided on December 23rd. An updated draft was distributed on January 8. Additional comments were received and posted on January 10 and 11.
11 | Closed | Develop initial list of data that the WEQ BPS would like to see for it to conduct analysis on the Parallel Flow Visualization project. | Steve Sanders Bert Bressers | 2010-12-01 | 2011-01-06 | 2011-01-11 | 1/11/11 - Bert Bressers provided a document on 1/7 to be reviewed by the BPS
12 | Closed | Request Rae McQuade send letter to NERC indicating NAESB has completed PFV Interim Solution and has no mechanism for requiring enitities to provide data to support interim solution | Ed Skiba/Kathy York | 2010-12-02 | 2010-12-17 | 2011-01-11 | Action item is dependent on input from James Culliton. The letter to NERC should indicate that the NAESB standards have 3 options BAs inside of markets with FERC approved Congestion Management Proccesses will continue to upload market flows (no change from current production environment). BAs outside of markets can either tag all non-firm transmission service or can upload generator priorities. Larry Kezele confirmed via email that NERC does not need a letter at this time. The subcommittee agreed to close this item. 1/11 - Kathy York to follow-up with Andy Rodriquez to confirm that NERC is planning on sending a letter to the impacted entities. If this is the case there is no need to pursue this action item.
13 | Closed | Identify what happens to capacity qualified units that bid into RPM but are not picked up. Do they retain DNR status? | Mike Colby | 2010-12-02 | 2011-01-11 | 2011-01-11 | 1/11 They retain their DNR status. To change their DNR status they would have to delist (request that they remove their letter or recallability.)
14 | Closed | What are the basic components needed in a Seams Agreement. | Ed Skiba Jim Busbin Steve Sanders Tom Mallinger Nelson Muller Bert Bressers | 2010-12-02 | 2011-01-11 | 2011-01-11 | This item should be included in the paper descibing the two-tier firm curtailment approach. It also should address how the seams agreement is different from what is included in the MOD standards. 1/11 - The basic components (minimum requirements for a seams agreement) were identified during the BPS meeting on 1/11 and will be posted as a work paper for the meeting.
15 | Closed | Send Revise Two-Tier Curtailment Document to NAESB for Posting and to request comments. | Ed Skiba | 2011-01-12 | 2011-01-12 | 2011-02-16 | Send Redline and Clean copy for posting 02/03 - Document was sent to NAESB office for posting on 1/12.
16 | Closed | Send request for comments on Two-Tier Curtailment Work Paper | NAESB Office | 2011-01-12 | 2011-01-14 | 2011-02-16 | Ed Skiba to contact NAESB office to determine if additional information is needed to send request for comments. 01/14 - Confirmed with J. Booe at NAESB that the workpaper could be posted for formal comments.
17 | Closed | Follow-up with Alan Johnson on comments provided for Hybrid Option to determine if any items can be closed based on discussions at December and January meetings | Ed Skiba | 2011-01-12 | 2011-01-14 | 2011-02-16 | 1/17 Held conference call with A. Johnson, P. Caulfield, and T. Mallinger. Based on discussion the NRG comments were removed from the document.
18 | Closed | Update Hybrid option and submit to NAESB for posting. | Ed Skiba | 2011-01-12 | 2011-01-17 | 2011-02-16 | 1/17 Document was sent to NAESB for posting.
19 | Closed | Update Objectives for BPS PFV Metrics | Chris Advena Tom Mallinger Bert Bressers Allan Pritchard Steve Sanders | 2011-01-12 | 2//9/11 | 2011-02-16 | Chris Advena will coordinate the effort. This item will be kept open pending the final recommendation. 2/16 - Document was provided and posted for 2/16-2/17 Meeting.
20 | Closed | Post draft minutes from July 15-16, 2010 WEQ BPS Meeting | James Culliton | 2011-01-12 | TBD | 2011-12-14 | Meeting minutes were posted on November 3, 2011
21 | Closed | Post draft minutes from September 15-16, 2010 WEQ BPS Meeting | James Culliton | 2011-01-12 | TBD | 2011-11-08 | Meeting minutes were approved by the BPS
21 | Closed | Post draft minutes from October 14-15, 2010 WEQ BPS Meeting | James Culliton | 2011-01-12 | TBD | 2011-04-11 | Minutes were posted on 3/31/11 and were approved on 4/11/11
22 | Closed | Post draft minutes from November 10-11, 2010 WEQ BPS Meeting | James Culliton | 2011-01-12 | TBD | 2011-11-08 | Meeting minutes were approved by the BPS
23 | Closed | Post draft minutes from December 1-2, 2010 WEQ BPS Meeting | James Culliton | 2011-01-12 | TBD | 2011-12-14 | Meeting minutes were posted on November 3, 2011
24 | Closed | Post draft minutes from January 11-12, 2011 WEQ BPS Meeting | James Culliton | 2011-01-12 | TBD | 2011-10-31 | 10/27 - Draft minutes have been posted.
25 | Closed | Post draft minutes from WEQ BPS Meeting February 16-17 | James Culliton | 2011-02-16 | TBD | 2011-10-31 | 10/27 - Draft minutes have been posted.
26 | Closed | Work with NAESB Office to confirm start/stop times for BPS 2011 meeting (meetings will not start before 8:00 Central time and will end at noon on the second day based on agreement at the December 1-2 BPS Meeting | Ed Skiba | 2011-01-12 | 2011-01-18 | 2011-02-16
27 | Closed | Identify locations for March - May BPS Meetings | Ed Skiba | 2011-01-12 | 2011-02-16 | 2011-02-16 | March Meeting Entergy Little Rock April Meeting Midwest ISO - Carmel May Meeting OATI - Minneapolis
28 | Closed | Provide IDC Working Group Update | Ben Taylor | 2011-02-16 | 2011-04-12 | 2011-04-12 | Update should include: - Status on change order for BAs to upload only Generator Priorities - SDX User Guide - Reliability metrics development - Status on entities providing data - Migration of Parallel Flow Visualization Interim Solution/Gen-to-Load to Production Servers Nelson Muller provided a status update in the April 28-29 Meeting.
29 | Closed | Write-up from the IDC Working Group on Change Order 283 | Ben Taylor/Nelson Muller | 2011-02-16 | TBD | 2011-12-15 | The write-up should explain what Change Order 283 accomplishes today, once full sets of data are provided under the Parallel Flow Visualization Interim Solution and what it may/may not accomplish under a permanent solution. 6/14 - Nelson will ask Yasser and Larry Kezele to add to next IDCWG Agenda. 7/12 - Nelson will bring up issue at the next IDC WG Meeting. 9/13 - A draft write-up will be developed at the October IDCWG meeting. Once finalized, this write-up will be presented to the WEQ BPS, likely in November. 10/12 - Draft summary document was provided to the BPS. The BPS members suggested areas where additional details could be added to the document. The IDCWG will update the document and make it available to BPS. 1/4/12 - Document was provided to the BPS at the December 15th meeting and is available at: http://www.naesb.org/pdf4/weq_bps121411w18.doc
30 | Closed | Develop Parallel Flow Visualization Presentation for ORS | Ed Skiba Narinder Saini Tom Mallinger | 2011-02-16 | 2011-04-25 | 2011-04-28 | Presentation will be developed after April 12-13 BPS meeting for the May 4-5 ORS Meeting. The presentation at a minimum needs to include: The Permanent Solution selected, the reason the option was selected, Change Order 310 is not needed for interim solution and whether it is needed for the Permanent Solution (if known at this time). 03/08 - A conference call will be scheduled for the BPS in late April to review the presentation before it goes to the ORS. 4/11 - There is a BPS meeting scheduled for April 28th, 29th when a presentation will be finalized. 4/29 - Presentation was reviewed by the subcommittee. It was noted in the review that the presentation was being provided by Tom Mallinger and was not endorsed by the BPS.
31 | Closed | Revised Two-Tier Curtailment Work Paper to remove the following sections and place in a position paper document: Review of Pro Forma Open Access Transmission Tariff (OATT) and Differences between Seams Agreements and MOD Standards Coordination Agreements | Ed Skiba | 2011-02-17 | 2011-02-21 | 2011-02-22 | Document was editted and posted for February 28th conference call.
32 | Closed | Provide updated Flowgate Allocation Detail Document. | Tom Mallinger | 2011-02-16 | tbd | 2011-04-04 | Decision was made to place this item on hold until the subcommittee completed work on the Two-Tier Curtailment Work Paper and associated position papers. 4/11 - Tom Mallinger submitted a revised flogate allocation details document
33 | Closed | Develop Summary Section describing what is two-tier curtailment to be included in work paper | Nelson Muller Tom Mallinger | 2011-02-22 | 2011-02-28 | 2011-02-28 | Document was reviewed during 2/28 conference call.
34 | Closed | Update two-tier curtailment work paper based on motions and discussion from February 22nd conference call | Ed Skiba | 2011-02-22 | 2011-02-28 | 2011-02-28 | On 2/28 a decision was made to move to a summary level document rather than to continue editting the detailed Two-Tier Curtailment Work Paper. 03/08 - The motion to remove the forward looking process for WECC needs to be addressed with the support paper.
35 | Closed | Post draft minutes from WEQ BPS Conference Call February 22 | James Culliton | 2011-02-22 | 2011-03-07 | 2011-03-09 | Meeting minutes will be discussed on March 9th.
36 | Closed | Post draft minutes from WEQ BPS Conference Call February 28 | James Culliton | 2011-02-28 | 2011-03-04 | 2011-03-08 | Draft Minutes were posted on March 4th.
37 | Closed | Schedule Breakout Session for to work on Position Papers during March 8th Meeting | James Culliton, N Saini | 2011-02-28 | 2011-03-07 | 2011-03-08 | Information was posted to the WEQ BPS Webpage
38 | Closed | Agree to level of detail to be included in the Two-Tier Curtailment Work Paper | All | 2011-02-28 |  | 2011-07-12 | Will be discussed at the March 8th meeting. 3/9 - There was general consensus to put this item on hold until after key topics have been discussed. The key topics are posted at: http://www.naesb.org/pdf4/weq_bps030811a2.doc 06/14 - The workpaper for the Two Tier Firm Curtailment (dated 2/28/11) and the support position paper and policy concerns papers for two tier curtailment will be posted as work papers for the July 12-13 WEQ BPS Meeting. Comments on the documents should be sent to NAESB by June 21st. The BPS co-chairs will have informal discussions on two-tier curtailment at the WEQ Leadership meeting on 6/22 and will provide an update to the BPS on July 12th. Alan Pritchard will take the lead developing a single policy concerns document by June 27-28. Those who feel that the items are not policy concerns can draft response for consideration. Ed Skiba will update the two-tier curtailment work paper prior to the July 12-13 Meeting. 07/29 - The subcommittee revised the document on 07/12 - There were no objections to forwarding the revised document to the Executive Committee.
39 | Closed | Develop Cover Letter for Two-tier curtailment and position papers | Ed Skiba, Narinder Saini | 2011-02-28 | tbd | 2011-08-09 | 3/9 = See item 38 for detail on why this item was placed on hold. 6/14 - See Comments on Item 38 07/29 - Draft of cover letter will be reviewed during August meeting 08/09 - Draft letter was created and posted.
40 | Closed | Add links to Two-Tier Curtailment work paper to include examples | Ed Skiba, Narinder Saini | 2011-02-28 | tbd | tbd | 3/9 = See item 38 for detail on why this item was placed on hold. 6/14 - See Comments on Item 38 07/29 - Examples were not included in the two-tier firm curtailment work paper. 08/09 - The subcommittee agreed this item could be closed. The examples were not included in the Two-Tier Curtailment Work Paper.
41 | Closed | Post draft minutes from WEQ BPS Meeting March 8-9 | James Culliton | 2011-03-09 | 2011-04-04 | 2011-04-11 | 4/11 - Meeting meetings were posted on April 8th and approved on April 11th
42 | Closed | Review Business Practice Standard Requirements document (Provide feedback to Ed Skiba) | All | 2011-04-12 | 2011-04-20 | 2011-04-28 | 4/19 - Document was posted on 4/13. Comments are due 4/20 4/28 - No Comments were received
43 | Closed | Post draft meeting minutes (April 11-13) | Ed Skiba | 2011-04-11 | 2011-04-20 | 2011-04-28 | 4/20 Minutes were posted on 4/18.
44 | Closed | Update Hybrid Option based on discussion from April 11-13 meeting | Ed Skiba | 2011-04-13 | 2011-04-22 | 2011-04-28 | 4/28 - The documents were posted 4/22
45 | Closed | Update Flowgate Option based on discussion from April 11-13 meeting | Tom Mallinger | 2011-04-13 | 2011-04-22 | 2011-04-28 | 4/28 - The documents were posted 4/22
46 | Closed | Check to determine what NAESB process could be used to approve the PFV permanent solution so that it can be used for the NERC ORS Parallel Test. | James Culliton | 2011-04-13 | 2011-04-28 | 2011-05-17 | 4/28 - The Parliamentary Committee is working through this issue 5/17 - Under Agenda item 5 meeting minutes Rae McQuade discussed the use of full staffing as an approach for supporting the NERC ORS Parallel Test.
48 | Closed | Update Hybrid Option Detail Document | Ed Skiba | 2011-04-29 | 2011-05-06 | 2011-05-17 | 5/6 - Document was posted for May 17-19 Meeting.
49 | Closed | Update Flowgate Allocation Option Detail Document | Tom Mallinger | 2011-04-29 | 2011-05-06 | 2011-05-17 | 5/6 - Document was posted for May 17-19 Meeting.
50 | Closed | Post April 28-29 Draft Meeting Minutes | Ed Skiba | 2011-04-29 | 2011-05-10 | 2011-05-17 | 5/7 Draft minutes were sent to NAESB to include voting record and attendance information and then post. 5/17 Final Meeting Minutes were approved by the BPS.
51 | Closed | Schedule review sessions for flowgate allocation and hybrid option for the week of May 9th | Ed Skiba | 2011-04-29 | 2011-05-05 | 2011-05-17 | Sessions were scheduled for May 9 (1:00 - 3:00 CDT) and May 11 (2:00 - 4:00 CDT)
52 | Closed | Notify WEQ EC Leadership that there are concerns that the Interim Solution does not address the NOI Docket RM10-09-000. | Ed Skiba | 2011-04-29 | 2011-05-17 | 2011-05-17 | 5/17 - This concern was raised to the WEQ EC chair on May 10th.
54 | Closed | Develop draft language for First-to-Curtail Requirements, Review and update Scenarios if needed, provide brief description explaining why the language is changing | Chris Advena, Nelson Muller, Shah Hossain, Bert Bressers, John Harmon, Steve Sanders, Ed Skiba, Narinder Saini, James Manning | 2011-06-15 |  | 2011-10-31 | Chris Advena will lead the First-to-Curtail Subteam. 07/29 - Discussion was held on 07/13. Proposed language and revised scenarios will be presented at the August meeting. 9/13 - Shah Hossain and Ed Skiba will assume co-leadership of this Subteam. 9/13 - The BPS co-chairs encourage the Subgroups to share their examples/work as soon as possible in the development process 10/31 - Completed review of Subteam's changes to the document.
55 | Closed | Provide First-to-Curtail subteam with latest graphics of first to Curtail Scenarios. | Ed Skiba | 2011-06-15 | 2011-06-17 | 2011-07-12 | 6/20 - Scenarios were sent to Chris Advena on 6/15.
56 | Closed | Provide updated spreadsheet inlcuded in Appendix A of Parallel Flow Visualization Permanent Solution Work Paper | Chris Advena | 2011-06-15 | 2011-06-23 | 2011-07-12 | 6/20 - Document was provided on 6/15 and included in the Parallel Flow Visualization Permanent Solution white paper on June 20th.
58 | Closed | Change all occurrence of off-the-path to off-path and all occurrences of on-the-path to on-path in the Parallel Flow Visualization Permanent Solution Work Paper. | Ed Skiba | 2011-06-15 | 2011-06-30 | 2011-07-12 | 6/20 - Changes were made to the document on June 20th.
59 | Closed | Research whether the PFV project will require changes to the WEQ 004 standards | N. Saini | 2011-09-13 |  | 2011-10-11 | 10/6 - Completed review of WEQ-004 and determined no changes were required. This was also confirmed with Clint Aymond (one of the co-chairs of the JESS). 10/11 - Reviewed with Subcommittee there were no issues with closing this Action Item.
60 | Closed | Research references to OASIS posting requirements in the White Paper | E. Skiba | 2011-09-13 |  | 2011-10-11 | 9/17 Response: There are two items related to posting on OASIS. These may be the same thing only worded differently: 1) Each Transmission Service Provider will post on OASIS their minimum requirements for considering firm use of transmission on their own system, according to their tariff. 2) Posting of methodology for establishing generator priority schedules and firm service. 10/11 - Based on this review the OASIS posting impacts would be limited to WEQ-001-013.
61 | Closed | Review and determine whether Permanent Solution would require any changes to the NERC IRO/INT/MOD and any other relevant NERC standards. Consider Parking Lot Item 4.2 | E. Skiba, N. Muller, N. Saini, S. Jones | 2011-09-13 |  | 2011-10-11 | 10/6 - Sub-team's review of NERC standards was posted as a work paper and is available at http://www.naesb.org/pdf4/weq_bps101111w7.doc 10/11 - The report was reviewed by the subcommittee. From the review the subcommittee passed motion 30, added action item 67, and added parking lot items 25 and 26.
62 | Closed | Check with the ORS leadership as to whether the ORS has an expectation that the BPS Permanent Solution be formally presented | E. Skiba, N. Saini | 2011-09-13 |  | 2011-10-11 | 9/19 - The ORS Chair has requested a BPS update be provided at the November 16-17 ORS Meeting. 10/11 - N. Saini will be presenting at the November ORS.
63 | Closed | Check whether White Paper -Outstanding Issues Not Addressed in Solution Item #1 can be withdrawn from consideration. The White Paper was updated by deleting the item. | E. Skiba | 2011-09-13 |  | 2011-10-11 | 10/6 - Analysis was posted as a work paper for the October 11-12 meeting. The work paper is available at. http://www.naesb.org/pdf4/weq_bps101111w4.docx 10/11 - Based on review of the document the subcommittee determined Item # 1 can be removed from further consideration.
64 | Closed | Will the current implementation of the PFV flow impact calculation (Gen to total BA load vs. native and transfer impacts) result in an equitable single “impact” calculation (from Parking Lot Item 5) | S. Sanders | 2011-09-13 |  | 2011-11-08 | 10/31 - Steve Sanders to develop some draft language for the white paper by 11/4. The subcommittee will review the language at the November 8-9 meeting. 12/14 - Steve developed paper which was reviewed during the November meeting. A subteam was created to review the two calculation methods. See action item 72. The subteam completed their review and Parking Lot Item 5 was resolved on December 14th.
65 | Closed | Change references from TSIN to webRegistry | E. Skiba J. Culliton | 2011-09-13 |  | 2011-10-11 | 9/17 Response: TSIN was replaced with TSIN/webRegistry and a footnote was added for clarification. 10/11 - Subcommittee reviewed changes and there were no issues with how the TSIN/webRegistry were referenced.
66 | Closed | Update White Paper to include Motion 29 | E. Skiba | 2011-09-13 |  | 2011-10-11 | 9/17 - The following statement was added to the white paper: A list of Coordination Agreements is not required to be posted on a Transmission Service Provider’s OASIS. 10/11 - Reviewed changes with subcommittee.
67 | Closed | Present Motion 30 to the Executive Committee at the October 25th meeting about elevating the priority of Interchange Standard Development to tag intra-BA Point-to-Point so that NERC addresses this item within 2012. This would also require a modification to IRO-006-EAST to modify R.3 and R.4 to support curtailment for intra-BA Point-to-Point. The timing for the changes to the INT and IRO standards will need to coincide with Parallel Flow Visualization moving into production. The NERC intra-BA tagging requirements should be coordinated with the NAESB Business Practices Subcommittee’s work on Parallel Flow Visualization. | E. Skiba N. Saini | 2011-10-11 |  | 2011-10-31 | 10/27 - Motion was presented to WEQ Executive Committee. The WEQ EC Chair and Vice-Chair have a conference call scheduled for mid-November and will raise this item with NERC at that time.
68 | Closed | Develop example of what the matrix would contain for TSPs identifying first to curtail and last to curtail. | N. Muller | 2011-10-11 |  | 1931-11-08 | 11/16/11 - Example was reviewed with Subcommittee on November 9, 2011.
69 | Closed | Consistently apply term GTL for gen-to-load and generation-to-load to the white paper | Ed Skiba | 2011-10-11 |  |  | 10/12 - Changes were applied to the document.
70 | Closed | Change all reference of Tranmission Provider to Transmission Service Provider. | Ed Skiba | 2011-10-11 |  |  | 10/12 - Changes were applied to the document.
71 | Closed | Incorporate status of Parking Lot Item 26 into White Paper. | E. Skiba | 2011-11-09 |  | 2011-12-14 | 11/16 - Common Requirement 5 was added to the White Paper. 12/15 The subcommittee reviewed the changes for Common Reequirement 5. There were no concerns raised with the proposed language so this action item is being closed.
72 | Closed | A subteam will conduct a table top analysis of the two impact calculations that are currently included in IDC Change Order 283 and make a recommendation to the subcommittee on whether we should begin the Parallel test with one of the calculations or both calculations after applying some suggested modification proposed by OATI. | Bert Bressers Nelson Muller Steve Sanders Shah Hossain Blaine Erhardt MISO tbd PJM tbd | 2011-11-09 |  | 2011-12-14 | Bert Bressers will lead this team. After reviewing the initial data the sub-team will provide a timeframe on when they can complete their work. Note: Shah Hossain will participate on the team provided there are no confientiality issues. 12/14 - Bert Bressers reviewed presentation from sub-team. Based on the review and update to Parking Lot item 5 this item is being closed.
73 | Closed | Provide to sub-team working on action item 72 available documentation that was used to move to two impact calculations | Tom Mallinger, Ed Skiba, PJM tbd | 2011-11-09 |  | 2011-12-14 | Providing data will require PJM releasing information to the sub-team 12/14 - Documents were provided to the sub-team and posted as work papers for the December 14-15 meeting.
74 | Closed | Subcommittee members should ask their legal staff if they have suggestions for how the IDC should treat discrepancies between dates provided or not provided for effective and/or termination dates of Coordination Agreements. | All | 2011-11-09 |  | 2012-01-18 | 12/14/11 - Who should be notified when an agreement is entered into the system or when an agreement is terminated Ask legal staff on notifications provisions when only one party enters either the effective date or termination? 2/16/12 - The Subcommitee included language in the white paper to use the latest effective date and the earliest termination date. As a result, this action item is being closed.
75 | Closed | Under Change Order 283 there is no restriction for a non-market entity or market entity to use either impact calculation. The subcommittee will move forward with both calculations allowing for the flexibility to use either calculation. The White Paper will be updated to reflect that a Balancing Authority can use either calculation method. | Ed Skiba | 2011-12-15 |  | 2012-01-18 | 1/18/12 The subcommittee reviewed and revised the language for Common Requirement 6 in the white paper that allows a BA to select either GTL impact calculation.
76 | Closed | Develop a template that identifies the criteria for possible scenarios for situations where there are differences in transmission service across multiple transmission providers from the physical location of the generation to the physical location of load. | Nelson Muller | 2011-12-15 |  | 2012-01-18 | 2/15/12 - The subcommittee reviewed the work paper for Action Item 76 and updated the status on Parking Lot Item 27. There was general consensus that this item could be closed.
77 | Closed | Look at potential approach for identifying the difference between intra-PTP tags and intra-network service tags. Develop recommendation for the BPS to review. | Nelson Muller | 2011-12-15 |  | 2012-01-18 | 1/18/12 The tags today have the capability to distinguish between intra-PTP and intra-network service.
78 | Closed | Present proposed Parallel Flow Visualization Solution to the JESS for them to determine if changes are needed to for WEQ-004, the e-tagging functional specification and/or the definition of interchange. | Ed Skiba Narinder Saini | 2011-12-15 |  | 2012-02-15 | Discussed with JESS on January 5, 2012. The JESS does not want to make changes to definition of Interchange. There are no changes needed for the Electronic Tagging Functional Specification. There is currently flexibility with the tagging system through product codes and miscellaneous tokens to support PFV. WEQ-004 could be modified to include Intra BA Transactions and a definition for Intra BA tranasctions could be added to WEQ-000. The JESS changes could be done during the full staffing phase of the Parallel Flow Visualization effort.
79 | Closed | Review prior meetings documentation to see if issues outlined in First -to-Curtail (FTC)/Last-to-Curtail (LTC) -- Other issues/questions 10/7/11, Steve Sanders (WAPA) have been discussed in prior meetings and if decisions where made to address any of the items. | Ed Skiba | 2011-12-15 |  | 2012-01-18 | 01/19/12 - Ed Skiba and Narinder Saini provided comments to the document that included historical references to prior documentation, which was reviewed by the subcommittee.
80 | Closed | Develop work paper on why Credit for Redispatch may not be needed if curtailments are based on current hour only. | Nelson Muller | 2012-01-18 |  | 2012-02-15 | 2/15/12 - Upon further review, Nelson determined there is a need for Credit for redispatch even if curtailments are based on current hour only. There is no need to develop or review a work paper.
81 | Closed | Apply resolution of Parking Lot Item 27 to the white paper | Ed Skiba Nelson Muller | 2012-02-16 |  | 2012-03-06 | 3/6/12 Changes were applied to the requirement sections and Appendix B was added to the White Paper
82 | Closed | Determine if IDC language is available in a public document that can be referenced for common requirement 10 (hierarchy for assigning generator output to transmission paths capacity for pseudo-ties) in the Parallel Flow Visualization Permanent Solution Whitepaper. | Roy True | 2012-04-03 |  | 2012-05-16 | 4/24 - Roy True did some research on available information. Based on this research, he is recommending that we move forward with existing language in the document.
83 | Closed | Revised Appendix B - Managing Pseudo Ties in the IDC so that it is consistent with the pseudo-tie language in the main body of the Parallel Flow Visualization Permanent Solution White Paper. | Nelson Muller | 2012-04-03 |  | 2012-05-16 | Ed Skiba to contact Nelson to have him revise Appendix B. 4/23 - Nelson Muller made changes to Appendix B.
84 | Closed | Identify level of detail provided to non-market BA's during TLR level 5 | Steve Sanders | 2012-04-03 |  | 2012-04-04 | Are inc/dec pairs provided to BA? 5/2 - Based on discussions on inc and dec generators and changes to remove references to inc/dec pairs can this item can be closed?
85 | Closed | Revise white paper to change reference of inc/dec pairs to inc and dec generators. | Ed Skiba | 2012-04-04 |  | 2012-05-16 | 4/9 - Document was reviewed. No additional changes were made for inc/dec pairs.
86 | Closed | Follow-up with Nelson Muller on comments in the white paper "Why beyond next hour? Take the best of all intervals." to determine if additional changes are require or if comments can be deleted. | Tom Mallinger | 2012-04-04 |  | 2012-05-16 | 5/2 - Nelson Muller confirmed the comments could be deleted. Comments were deleted in the white paper.
87 | Closed | Replace Approaches for Meeting Relief Obligations in Appendix A with language in Common Requirement 2 | Ed Skiba | 2012-04-04 |  | 2012-05-16 | 4/9 - Section was updated in Appendix A.
88 | Closed | Do consistency checks for cases in Appendix A | Ed Skiba | 2012-04-04 |  | 2012-05-16 | 4/9 - Minor changes were applied to Appendix A.
89 | Closed | Develop language on the treatment of Inter and Intra BA point-to-point tags and Inter BA network service tags being moved to subpriority S4 (and other subpriorities). Need to check for consistency of all sub-priorities so that it does not create conflicts. | Nelson Muller Tom Mallinger | 2012-05-16 |  | 2012-08-27 | Will report back at the next meeting 07/18 - Sub-team will discuss on July 19th and report back to the full BPS at the August meeting. 8/15 - Date moved to August 27th conference call when subpriority examples will be discussed. 9/12 - The BPS determined no further work needed on assigning subpriorities work paper. Remaining work to modify WEQ-008 will be addressed under Action Item 95
90 | Closed | How will one offs made to the IDC that impact the GTL calculations that were added to the IDC since the Change Order 283 was accepted be included in the PFV Permanent Solution Parallel Test environment such as EAR Tag, and Michigan Ontario PARs. | Yasser Babhaz | 2012-05-16 |  | 2012-10-17 | Discussed with the IDCWG on May 17th. Yasser will report back to the BPS after the next IDCWG meeting. 7/18/12 Ed will work with Yasser to determine if there is a possibility for video conferencing/web conferencing to discuss this and other items for the afternoon of August 15th since both groups will be meeting. 8/15/12 - Will be discussed at the October Face-to-Face Joint meeting. 9/12 - Yassir provided update on how one offs would be addressed. The EAR can be possibly addressed based on how the resource is modeled in the IDC.
91 | Closed | Move Items to Be Addressed During the Field Test from Appendix A to the Summary of items to be addressed during the Parallel Operations. | Bert Bressers | 2012-05-17 |  | 2012-06-13 | 6/13 - Items were moved to the work paper that identifies items to be tracked during the Parallel Operations. 6/13 - After additional discussion the decision was made to keep the items in Appendix A.
92 | Closed | Add to items to be tracked during the Parallel Test- determine if relief obligations are being met through other mechanisms such as counter flows as load displacement. | Bert Bressers | 2012-05-17 |  | 2012-06-13 | 6/13 - Item was added to work paper that identifies items to be tracked during the parallel operations. 6/13 - After additional discussion a decision was made to move item to Appendix A.
93 | Closed | Follow-up with Rae McQuade on ability for NAESB to approve IDC change order for Parallel Flow Visualization | Ed Skiba | 2012-05-17 |  | 613/12 | Informal comments can be provided through a joint working session. Sending formal comments would require EC and Managing Committee approvals. Ed to follow up with Larry and Yasser to see if informal comments in a meeting would suffice as feedback on the PFV change order. 6/13 - Confirmed with Larry Kezele and Yasser Babhaz that the BPS will provide feedback on the change order during a joint session review of the Change Order.
94 | Closed | Identify IDCWG resources to help define subpriority requirements for tags | Yasser Babhaz | 2012-05-17 |  | 2012-07-18 | Tom Mallinger will follow-up with Yasser 6/13 - Need additional follow-up with Yasser on how the IDC Working Group will participate in the Subpriority discussion. 7/18/12 - IDCWG members have begun participating in meetings starting on 6/26/12.
97 | Closed | What data is available for the BPS to review during the Parallel Operations (Full Staffing) | Yasser Babhaz Ed Skiba | 2012-06-13 |  | 2012-09-12 | 6/13 - Item was initially discussed during the May 17th Joint meeting. Yasser is to provide an update at the BPS July 18-19 WEQ BPS meeting. 7/18/12 - The IDCWG has not discussed this item. Ed to follow-up with Yasser to determine if this can be discussed during a joint session on August 15th. 8/15/12 - The IDCWG has not yet discussed this item. It is to be discussed during their August 15-16 meeting. Will request an IDCWG Update for the September meeting. 9/12 - The IDCWG can provide statistical data based on % changes between the production system and the PFV/GTL system at a BA level. It won't identify a specific BA or flowgate.
98 | Closed | Provide suggested editorial changes to the PFV White Paper | Tom Mallinger, Steve Sanders | 2012-06-14 |  | 2012-09-12 | 7/18/12 - Tom provided comments on proposed language for phrases such as "BA shall meet its relief obligations." Changes needed to be included in the white paper and recommendation where appropriate. Narinder will follow-up with Steve Sanders to determine what edits he wants to propose. 8/15 - Waiting on response from Steve. The BPS agreed we can close this item 9/12 - No response from Steve
99 | Closed | Modify working copy of White Paper to reflect that it is the BA not theTSP that elects to use the Tag All Non-firm or Generator Prioritization Component | Ed Skiba | 2012-06-14 |  | 2012-07-18 | 7/18/12 - Changes were included in the white paper that was posted for the July 18-19 WEQ BPS meeting.
101 | Closed | Follow-up with IDCWG on the assumption "All generating resources in the EMS model will be included in the Parallel Flow Visualization process. If a generator is in the EMS model it should also be in the IDC model. This will include pseudo-ties. | Larry Kezelle | 2012-07-18 |  | 2012-09-12 | 8/15/12 - Need to check with Larry to see if the IDC will support having all of the generating resources in the IDC as a part of PFV. We know all resources are not currently modeled in the IDC. If not the BPS will need to assess the impact of not having all generating resources for the PFV project. 9/12 - We confirmed with Yasser that the IDCWG is working under the same assumption that the BPS is.
102 | Closed | Follow-up with JESS on the definition of Interchange Transaction that includes "Seller" vs "seller". | Ed Skiba | 2012-07-18 |  | 2012-08-15 | 8/15/12 - Seller was lower cased in the Version 3.0 standards which was published on July 31st.
103 | Closed | Have Credit for Redispatch sub-team review WEQ-008 section (s) on subpriorities and determine if their work on subpriorities will/should be included in WEQ-008. | Ed Skiba Tom Mallinger Nelson Muller | 2012-08-15 |  | 2012-09-12 | 9/12 - This item is closed based on the changes made to WEQ-008
104 | Closed | Develop an example of how firm generator output is determined when a generator is providing output to multiple local BA/zones (load) and some of the output is reported as non-firm. | N. Saini | 2012-08-15 |  | 2012-09-12 | 9/12 - The subcommittee walked through the examples provided
105 | Closed | How/where are local BAs/Zones defined | N. Muller | 2012-08-15 |  |  | Is this defined in the EIR and flows to the IDC? 9/13 - Currently local BAs/Zones defined in book of flowgates
108 | Closed | Talk with JESS to inform them that the PFV solution includes tagging all pseudo ties. As a result of this decision the tag will need to have an indicator that it is for a pseudo-tie. | E. Skiba | 2012-08-16 |  | 2012-09-12 | 9/12 - Confirmed with JESS that there is an indicator to identify pseudo-tie tags.
109 | Closed | Identify lead fo sub-team working on the IDC support document to be included with the recommendation. | N. Saini | 2012-08-16 |  |  | 9/12 - Frank Koza will be the lead
112 | Closed | Determine if Section 3.11 (Parallel Flow Calculation Procedure for Reallocating or Curtailing Firm Tranmission Service [the backup calculation]) will be needed once PFV is implemented. If yes, what changes are needed for PFV? First, will it include First-to-Curtail and Last-to-Curtail? Second, will it include Credit for Redispatch? Third, will it include subpriorities for Firm and non-Firm? Fourth, is it limited to the GTL calculation only or does it effect tags? Fifth, when will the calculation be used? | N. Muller | 2012-09-12 |  | 2012-09-13 | 9/13 - The subteam will remove Section 3.11 from the standards for PFV